## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2181-swen-261-08-a- TeamA
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | PJ, MR 10/12
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | PJ, MR 10/12
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | MR, AC, 10/12
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | PJ, 10/11 HTML5 field validation (and backend 11/03)
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | MR, 10/13
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | AC, 10/14
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | AC, 10/14
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | PJ, AC 10/13
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | AC 10/13
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | AC 10/22
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | AC 10/22
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | AC, MR 10/31
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | PJ, 10/31
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | AC, DO 11/2
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | AC 11/2
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | PJ 11/2
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | AC, DO 11/2
As a player I want to do a simple checkers move so that my piece can move to the adjacent red square. | Given a player wants to move their piece when the location of the movement is forward and diagonal then that piece should be moved to that location. | Pass | DO 11/7
| Given a player wants to move their piece when the location of the movement is occupied then that piece should not be moved to that location. | Pass | AC, DO 11/2
| Given a player wants to move their piece when the location of the movement is not occupied then that piece should be moved to that location. | Pass | AC, DO 11/2
| Given a player wants to move their piece when the location of the movement is backwards then that piece should not be moved to that location. | Pass | AC, DO 11/2
| Given a player wants to move their piece when the location of the movement is more than one square away then that piece should not be moved to that location. | Pass | AC, DO 11/2
| Given a player wants to move their piece when the location of the movement is forward but not diagonal then that piece should not be moved to that location. | Pass | MR, PJ 11/5
| Given a player wants to move their piece when the location of the square is the same color of the square it originated from then that piece should be moved to that location. | Pass | DO 11/5
| Given a player wants to move their piece when the location of the square is a different color then that piece should not be moved to that location. | Pass | DO 11/5
As a player I want to be able to capture the other player's piece by jumping over it so that I land on the next red square after the other player's piece and I capture their piece. | Given a opponent’s piece is in the diagonal square and the next forward adjacent square is free when the user wants to move a regular piece, then the piece should be moved there. | Pass | PJ 11/7
| Given that an opponent's piece is in the forward diagonal square and another opponent's piece is in the the next forward diagonal square, when the user tries to jump over the two or more pieces, then the piece should not be moved there. | Pass | DO, AC 11/7
| Given a simple jump move was made, when the user lands on the next square then the opponent's piece that was previously in the forward diagonal square should be captured. | Pass | DO 11/7
| Given a piece can make a simple jump when it is this player's turn, then that move has to be made. | Pass | AC, DO 11/7
As a player I want to be able to make a multiple jump move following the multiple jump rules so that I capture multiple of the other player's pieces and move my piece through multiple jumps. | Given that a piece was captured and that there is a valid jumping square When the user jumped a piece forward, Then the user can jump that piece forward again. | Pass | DO, AC 11/17
| Given that another of the opponent's pieces is available to capture when a player finishes a jump, they must capture that opponent's piece | Pass | AC, DO 11/7
| Given that a piece is attempting to make a move, when the move is a backwards jump, the move will not occur. | Pass | MR, DO 11/7
As a Player I want to be able to move a piece to a spot on the board only if it is a valid move so that I don't violate any rules and play the game correctly. | Given that a Player is in a game of checkers, when that player clicks on a white square then that square is not interactable | Pass | MR, 11/7
| Given that it is a player's move when they drag a piece on an occupied square then that piece should not be droppable | Pass | PJ 11/7
| Given that a player is making a jump move, when the player picks the next diagonal black square, then the piece should be droppable | Pass | DO 11/7
| Given that a player is making a simple move, when the player picks an unoccupied adjacent black square, then the piece should be droppable | Pass | DO 11/7
| Given that a player's piece has not been kinged, when the player clicks a square behind where the piece is, then that square should not be interact-able and/or the piece should not be droppable | Pass | DO, AC 11/7
| When a player makes a jump move, when there are more valid jump moves available, then that player should not be allowed to end their turn | Pass | MR, DO 11/7
As a Player I want to be able to move my pieces to the other side of the board and "king" my piece so that I can now move my piece backwards as well as forwards. As a Player I want to be able to move my pieces to the other side of the board and "king" my piece so that I can now move my piece backwards as well as forwards. As a Player I want to be able to move my pieces to the other side of the board and "king" my piece so that I can now move my piece backwards as well as forwards | Given a piece reaches the the the opponents end of the board when the move has just ended then the piece should become a King. | Pass | DO 11/25
| Given a piece reaches the the the opponents end of the board when the move has just ended then the turn should end. | Pass | AC, DO 11/28
| Given a piece is a king when a move is made then that move has to be diagonally forward or backward. | Pass | PJ, DO 11/29
| Given a piece is a king when a move is made then the location of the move cannot be already occupied. | Pass | DO 11/25
| Given a piece is a king when a jump move is made then the jump can be forward or backward following the rules established for a jump. | Pass | DO, MR 11/29
As a Player I want to be able to see what piece my opponent moved and the start and end position of the move so that I can clearly see my opponents move and not just infer from the end state. | Given that it is my opponents turn when I log out, if they make a move when I log back in then I expect it to be my turn and see their move. | Pass | AC, 11/25
| Given that it is my turn when I log out and log back in then I expect to see the last move in my turn. | Pass | AC 11/25
| Given that it is my opponents turn and they do not make a move when I log out and log back in then I expect it still be their turn. | Pass | AC, MR 11/25
| Given that it is my opponents turn when I log out, if they make a move when I log back in then I expect it to be my turn and see their move. | Pass | AC, MR 11/25
As a Player I want to access a menu of my past games so that I can select one and view the game to learn from my past mistakes. | Given I am on the home page, when I click a "view past games", then I can expect to see a list of the past games. | Pass | AC, PJ 11/27
| Given I am viewing the list, when I click "go home" then I can expect the application to take redirect me back to homepage | Pass | MR 11/27
| Given I am viewing the list of past games, when I click on on of a link in the list, then the application should build "replayGame.ftl" and take to past game page. | Pass | PJ 11/27
As a Player I want to see where the pieces were at X move last game so that I can see what move I made during that game. | Given I am on a page of viewing a past game, when I click "next", I should be able to see an updated board state with the next move placed. | Pass | MR, DO, 11/29
| GIven I am on a page of viewing a past game, when the it is the beginning of a game, the "previous" button should be deactivated. | Pass | AC, PJ, 11/29
| Given I am on a page of viewing a past game, when the it is the end of a game, the "next" button should be deactivated. | Pass | AC, MR, 11/29
As a Player I want to be able to stop reviewing my old games so that I can go back to my current game or just look at another game/see the main lobby. | Given I am on the home page, when I click "exit", then I can expect to go back to the list of all past games. | Pass | AC 11/27
| Given I am viewing a past game, when I click "my home", then the application should take me back to the home page. | Pass | AC 11/27
| Given that I am viewing a past game, when I want to stop viewing that game, I should be able to exit at any state of the board/any state of moves. | Pass | AC, PJ 11/27